PrepHQ

Document 06 — Implementation Plan

Version 1.0 | PrepHQ EdTech App

# Overview

Solo developer build. Estimated MVP to launch: 10–12 weeks. Priority is web first, then mobile. Ship fast, validate with 100 paying users, then iterate.

# Phase 1 — Project setup (Week 1)

- Init Next.js 14 project with TypeScript + Tailwind CSS

- Init Expo React Native project with TypeScript

- Connect Supabase — create project, set up database, enable Auth

- Configure environment variables on Vercel and local .env

- Set up GitHub repo with /web and /mobile folders

- Configure ESLint, Prettier, and Husky pre-commit hooks

- Deploy empty Next.js app to Vercel (get live URL early)

# Phase 2 — Database (Week 2)

- Write all migration files: users, exams, questions, user_exam_access, mock_attempts

- Seed exams table with JAMB, WAEC, NECO, Post-UTME rows

- Seed 50 sample questions per exam for development

- Set up Row Level Security policies on all tables

- Test RLS with multiple test user accounts

- Set up Supabase Storage buckets

# Phase 3 — Auth (Week 3)

- Implement signup/login/logout on web (email + Google OAuth)

- Implement onboarding flow — exam selection, role picker (student/parent)

- Implement protected route middleware in Next.js

- Implement parent account linking (student ID input + DB update)

- Mirror auth flow on React Native mobile (Expo AuthSession for Google)

- Test session handling, refresh tokens, and logout across devices

# Phase 4 — Payments (Week 4)

- Integrate Paystack on web — one-time payment per exam

- Build /pay/[exam] page with exam details and Paystack popup

- Set up Paystack webhook endpoint to verify payment and update user_exam_access

- Add payment success/failure redirect and toast notifications

- Test card, bank transfer, and USSD payment methods

- Implement exam access gate — middleware checks user_exam_access before loading exam pages

# Phase 5 — Question bank & mock exam (Weeks 5–6)

- Build subject picker page /exams/[exam]/subjects

- Build past questions browser /exams/[exam]/history with year + subject filters

- Build timed mock exam engine — load questions, track answers in state, countdown timer

- Auto-submit on timer expiry, save to mock_attempts

- Build results page — score, per-subject breakdown, correct/wrong answer review with explanations

- Mobile: build same exam flow in React Native with swipe navigation between questions

# Phase 6 — Dashboards (Week 7)

- Build student dashboard — unlocked exams, recent mock scores, weak subject highlights

- Build progress charts using Recharts — score over time per exam

- Build parent dashboard — linked student's stats, study time, mock history

- Weekly email summary to parents via Supabase Edge Function + Resend

# Phase 7 — Offline mode (Week 8)

- Implement question pack downloads using Expo SQLite

- Build /offline page — shows downloadable packs per exam, storage usage

- Add network detection — show offline banner, switch to local SQLite when offline

- Background sync — push any completed offline attempts to Supabase on reconnect

# Phase 8 — UI polish (Week 9)

- Apply full design system — colours, typography, spacing, border radius

- Add loading skeletons on all data-fetching screens

- Build all empty states — no exams unlocked, no attempts, no downloads

- Build all error states — payment failure, network error, session expired

- Responsive design audit — test on 320px, 375px, 768px, 1280px breakpoints

- Accessibility — keyboard navigation on web, screen reader labels on mobile

# Phase 9 — Testing (Week 10)

- Manual test all user flows: student journey end-to-end, parent journey end-to-end

- Test payment flows — success, failure, webhook retry

- Test offline mode — airplane mode mid-exam, reconnect sync

- Test RLS — confirm users cannot access other users' data

- Performance test — Lighthouse score > 85 on web, profiling on low-end Android

- Bug bash — fix all critical and high severity issues before launch

# Phase 10 — Launch (Weeks 11–12)

- Configure custom domain (prepHQ.ng or similar)

- Set up production environment variables on Vercel and Supabase

- Submit mobile app to Google Play Store (Android first, iOS later)

- Seed full question bank — minimum 500 questions per exam before launch

- Set up Paystack production keys and test live payments

- Soft launch to 50 beta users — collect feedback via Tally form

- Fix beta feedback issues, then public launch

# Done criteria

| Feature | Done when… |
| --- | --- |
| Auth | User can sign up, log in, and log out on web and mobile |
| Payments | Student can pay for an exam and immediately access all content |
| Mock exam | Student can complete a full timed exam and see results with explanations |
| Parent dashboard | Parent can link to child and see live stats |
| Offline mode | Student can download and complete a mock exam with no internet |
| Launch | 100 paying users in first 2 weeks post-launch |